## 457b Long Term Plan
457(b) Retirement Readiness 3 year plan
| Goal 1 - Joel | Goal 2 - Jenn | Goal 3 - Terry | Goal 4 - Patty | Goal 5 - Patty
| Improve Employer Participation | Increase Savings Rate of Younger Participants | Increase Enrollments in 457(b) | Retain Terminated Participants | Create Retirement Friendly 457(b) Plan
12-month goal(s) | Reach out to all non-participating employers with 10 or more employees. Survey non-participating employers to learn why they are not participating. | Develop educational campaigns to enable Millenials and Gen Z participants to increase 457b saving rates | Conduct surveys to targeted groups to learn why individuals are not participating in 457b. Conduct survey for participating employers to learn their level of understanding of the 457b plan and resources. | Survey individuals whom refunded their 457b accounts to understand why they left the plan. Determine if MPERA will adopt Empowers retirement readiness advice services; if so, execute adoption within 12 months. | Optimize investment menu. Determine if MPERA wants to adopt Empower retirement readiness advice services. Determine the distribution of our members in relation to Retirement Tiers 1-3.
3-year goal(s) | On an annual basis, measuring number of employers who transition, 2 employers per year. | Observe 5% of participants increase their 457b savings. Identify successful outreach techniques. | Observe 5% increase in 457b enrollments per year for 3 years. Identify successful outreach techniques. | Increase 5% of rollovers into the plan. Decrease 5% of rollovers out of the plan. Identify successful outreach techniques. | Determine the optimal engagement level of the 457(b) plan
Strategies | Education campaigns, survey, employer outreach | Education campaigns, 1:1 meetings, retirement education/webinars | Surveys, retirement education/webinars, education campaigns, 1:1 meetings, employer outreach | Surveys, retirement education campaigns highlighting resources available, offer retirement readiness review/advice sessions via 1:1 meetings | Surveys, evaluation of investment menu, review of advice services, review and enhance education and tools
Measurements | Observable rate of increase in employer participation [minimum of 6 employers over 3 years] | Observable rate of increase in savings as a direct result of strategies deployed | Observable rate of increase in enrollments as a direct result of strategies deployed | Observable rate of increase in rollovers into the plan/decrease of rollovers out of the plan as a direct result of strategies deployed | Thorough review and completion of Plan Sponsor Checklist including: Plan functionality, Tools, Education, Investment Menu, Default Option, Advice
Project Tasks for Year 1 of 3
January 2022 - December 2022
Project Goal | Task | Assigned To | Estimated Start Date | Estimated Finish Date | Priority | Notes | Action Items
Goals 1 and 3 | Conduct employer query to ID the best contact at each location for survey | MPERA Education | 2021-11-01 | 2021-12-31 |  | Need to identify the most appropriate contact for employer surveys for usable/strong data. This will likely be different for each employer. | Run primary and secondary active contacts in PERIS for each Org.
Goal 1 | Create survey for non-participating employers to learn why they may not be participating | MPERA Education and Empower | 2021-11-01 | 2021-12-31 |  |  | Joel to research/create questions. Ask Empower for similar surveys from other contracts.
Goal 1 | Conduct survey for non-participating employers to learn why they may not be participating | MPERA Education | 2022-01-15 | 2022-02-15 |  |  | Release survey via Survey Monkey (purchase survey monkey license) using Gov Delivery
Goal 1 | Explore the opportunity to have quarterly OR bi-annual Employer meeting to discuss customer service and plan satifaction and improvement. Discuss onboarding and plan communication. | MPERA EDUCATION | 2022-02-01 | 2022-12-31
Goals 1 and 3 | Review survey data (non participating employer; participating employer) | MPERA Education and Empower Marketing Staff, RVK | 2022-02-15 | 2022-03-01 |  | Extract usable data from each survey to determine new/revised education, education campaigns | Education to complete initial review, bring in Empower Marketing to review for additional content to letter (if necessary). Review survey data for participating employers to develop educational campaigns for employers.
Goal 1 | Develop a "Why Join" Letter recruiting Employers | MPERA Education and Empower Marketing Staff | 2022-03-01 | 2022-03-31 |  | This letter should highlight the benefits for employees who elect to join 457b | Use existing 'Why Join' doucment developed in 2021. Add additional information as needed, based on survey data.
Goal 1 | Release "Why Join" Letter to Employers | MPERA Education | 2022-04-01 | 2022-04-01 |  |  | Deliver to employers via email.
Goals 1 and 3 | Employer Spring Training - Highlight 457b Plan Education | MPERA Education | Mid/Late April | Mid/Late April |  |  | Provide employer 457b education as a part of employer spring training week
Goal 1 and 3 | Create and release follow up letter to non-participating Employers | MPERA Education | 2022-05-15 | 2022-05-30 |  | Offer to provide education to employer, answer question | Follow up email to non-participating employers with regard to 457b
Goal 1 | Report new employer 457b participation to Board and EIAC at year end | Patty | 2022-12-01 | 2022-12-31
Goal 2 | Create survey for individuals under age 35 whom are participating in 457(b) | MPERA Education and Empower Field/Marketing Staff | 2022-02-01 | 2022-03-31 |  | Why are individuals not invested in TDF? What is driving low 457b savings rates? Are members investing elsewhere? Do members lack understanding of optimal savings rates? Do members have lack income? Survey to learn more about this demographic of members and to determine next steps to assist in increased savings | Meeting(s) with MPERA Education, Empower Field Team, and Empower Marketing Team to discuss observed behaviors of younger participants and develop survey questions (referencing other plan surveys)
Goal 2 | Conduct survey for individuals under age 35 whom are participating in 457(b) | MPERA Education and Empower Marketing Staff | 2022-04-01 | 2022-04-30 |  |  | Empower to deliver survey via Survey Monkey
Goal 2 | Review survey data (younger participants) | MPERA Education and Empower Marketing Staff | 2022-05-01 | 2022-05-31 |  | Extract usable data from each survey to determine new/revised education, education campaigns | Review data with Empower Marketing to develop an increase savings campaign
Goal 2 | Establish educational campagins for 2022 | MPERA Education and Empower Marketing Staff | 2022-01-15 | 2022-02-15 |  | Based on data provided in Empower Study - Participant Behavior by Generation
Goal 2 | Develop increase 457b savings campaign for NRSM | MPERA Education and Empower Marketing Staff | 2022-06-01 | 2022-08-01
Goals 2-3 | NRSM Campaigns | MPERA Education and Empower Field Staff | Mid October | Mid October
Goal 2 | Year end review | MPERA Education and Empower Field/Marketing Staff | 2022-12-01 | 2022-12-31
Goal 3 | Connect with Yellowstone County to learn about their experience transitioning to State of MT 457b, their ongoing success and struggles | MPERA Education and Empower Field Team | 2021-10-01 | 2021-11-15 |  | Ask Yellowstone County: What was their motivation to join State of MT 457b plan? What is important to the employer? Where are our blind spots? How can we (MPERA/Empower) improve; administratively, services, resources, education, etc.? | MPERA Edu (Terry) and Empower Field (Julie) to coordinate
Goals 1 and 3 | Conduct employer query to ID the best contact at each location for survey | MPERA Education | 2021-11-01 | 2021-12-31 |  | Need to identify the most appropriate contact for employer surveys for usable/strong data. This will likely be different for each employer. | Run primary and secondary active contacts in PERIS for each Org.
Goal 3 | Create survey for participating employers to understand the employers level of understanding of the 457b plan | Liz, Scott, Empower Field Staff, MPERA Education | 2021-10-15 | 2021-12-31 |  | Empower to help develop these survey questions based on their experiences with other plans
Goal 3 | Conduct survey for participating employers | MPERA Education | 2022-01-15 | 2022-02-15 |  |  | Release survey via Survey Monkey (purchase survey monkey license) using Gov Delivery
Goals 1 and 3 | Review survey data (non participating employer; participating employer) | MPERA Education and Empower Marketing Staff | 2022-02-15 | 2022-03-01 |  | Extract usable data from each survey to determine new/revised education, education campaigns | Education to complete initial review, bring in Empower Marketing to review for additional content to letter (if necessary). Review survey data for participating employers to develop educational campaigns for employers.
Goals 1 and 3 | Employer Spring Training - Highlight 457b Plan Education | MPERA Education | Mid/Late April | Mid/Late April |  |  | Provide employer 457b education as a part of employer spring training week
Goals 1 and 3 | Create and release follow up letter to participating Employers | MPERA Education | 2022-05-15 | 2022-05-30
Goal 3 | Create survey for individuals who are NOT participating in 457(b) individuals under 35 and new hires over 35 | MPERA Education and Empower Field/Marketing Staff | 2022-06-01 | 2022-07-01 |  | Ask for demographic info in the survey. | Ask Empower if they have previous survey questions to leverage.
Goal 3 | Run query for non-participating and eligible 457b participants under 35 and new hires over 35 | MPERA Education | 2022-06-01 | 2022-07-01 |  |  | Query in PERIS
Goal 3 | Conduct survey for individuals who are NOT participating in 457(b) | MPERA Education | 2022-07-01 | 2022-07-30 |  |  | Via Gov Delivery using Survey monkey
Goal 3 | Review survey data | MPERA Education and Empower Field/Marketing Staff | 2022-08-01 | 2022-08-15 |  | Extract usable data from each survey to determine new/revised education, education campaigns | Education to complete initial review, bring in Empower Marketing to review for additional content to letter (if necessary)
Goal 3 | Develop 457b enrollment campagin for NRSM | MPERA Education and Empower Field/Marketing Staff | 2022-08-15 | 2022-09-15
Goals 2 - 3 | NRSM Campaign | MPERA Education/Empower Field Staff | Mid October | Mid October
Goal 2 | Year end review | MPERA Education and Empower Field/Marketing Staff | 2022-12-01 | 2022-12-31
Goal 3 | Start conversations with employers about how to engage and connect with all new hires regardless of age | MPERA Education | 2023 | 2023 |  | NEOs are a key variable to initial engage with new hires. Suggested to follow up with new hires shortly after NEOs. Younger generations are connecting with data that demonstrates the importance of saving now versus later. Compounding interested over time is resonating with younger generations. Strengthen relationship with Employers to lead to greater engagement with employees. | Maybe Feb 2023 Fall in Love with 457b Campaign?
Goal 3 | Develop a correspondence plan for all new hires | MPERA Education and Empower Marketing Staff | 2023 | 2023 |  | Develop plan for correspondence for new hires. How often should MPERA reach out to new hires? Every 3, 6, 9 months? How should the correspondence be delivered? Younger generations - consider e-mail, social media, videos, etc. What should it include? This effort can be combined with new hire plan choice election correspondence. Separate communication for other retirement systems. | Maybe Feb 2023 Fall in Love with 457b Campaign?
Goal 4 | Learn how Empower interacts with terminating individuals (with and without RSG/Retirement Advice Services) provide options, final deferral, stay in the plan, distribution options. We do not get term dates, only know an employee is terminating when they reach out. Can MPERA input term dates on a monthly basis, or provide list of term'd ppts? We are losing assets due to uninformed participants - lack of communication. | Empower Field Team and MPERA | 2022-01-01 | 2022-03-31 |  | Learn about Empowers field experience, understand the conversation between Empower/Member | Bi-weekly field team meeting - Empower to educate MPERA
Goals 4 and 5 | Evaluate Empowers available channels for requesting distributions (functionality) | Empower/Chris Heisel | 2022-01-01 | 2022-03-31 |  | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
Goals 4-5 | Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) what age group/all age groups? phone or form, installment payments, one time lump sum cash out vs. rollover | Empower/Brett Fisher | 2022-02-01 | 2022-03-31
Goal 4 | Identify individuals who refunded their 457b account in the last 36 months include age, distribution amount/portion of account (did they set up p-pay or lump sum) | Empower/Julie Lucas | 2022-01-01 | 2022-01-31 |  | Did COVID influence termination and refunds? | Empower/MPERA mgmt to determine query of refunded individuals
Goal 4 | Create survey for individuals who refunded their 457b account in the last 36 months | Empower | 2022-01-01 | 2022-02-28
Goal 4 | Conduct survey individuals who refunded their 457b account in the last 12 months. | Empower | 2022-03-01 | 2022-03-31 |  | Begin to understand why terminated individuals leave the plan. Are pre-retirees aware of the Plan's partial distribution features? Are they aware of retirement resources available to them (counselors, webinars, and tools)?
Goal 4 | Review survey data | MPERA, Empower, RVK | 2022-04-01 | 2022-04-30 |  |  | Timeline prepares us to launch new campaign, tools, etc for 2023
Goals 4-5 | Present Retirement Readiness Review/Advice Option to EIAC (investment options) | Liz | 2021-10-28 | 2021-10-28 |  | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
Goals 4-5 | Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | Patty/Liz | 2021-12-09 | 2021-12-09
Goals 4-5 | If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | Empower Marketing Staff | TBD | TBD
Goals 4-5 | If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | MPERA education and Empower Field Staff | TBD | TBD
Goals 4-5 | Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | MPERA education and Empower Field Staff | TBD | TBD |  | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
Goals 4-5 | Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | Empower | TBD | TBD |  | EIAC meeting with RRR
Goals 4-5 | Website expected update - Empower (edu and tools) | Empower | TBD | TBD |  | When is the rollout of the new/update website expected?
Goal 5 | Review investment menu (investment options) | MPERA, EIAC, RVK, PRB | 2021-10-01 | 2022-10-01 |  | Investment menu is currently under review. Does the plan offer a range of investment solutions suitable for retirees? Is the Plan's default investment option suitable for retirees?
Goal 5 | Review plans fees and relative competitiveness for retirees (investment options) | MPERA, EIAC, RVK, PRB | 2021-10-01 | 2022-10-01 |  | Completed with recent fee changes? OR was this to target younger participants?
Goals 4 and 5 | Present Retirement Readiness Review/Advice Option to EIAC (investment options) | Liz | 2021-10-28 | 2021-10-28 |  | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
Goals 4 and 5 | Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | Patty/Liz | 2021-12-09 | 2021-12-09
Goals 4 and 5 | If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | Empower Marketing Staff | TBD | TBD
Goals 4 and 5 | If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | MPERA education and Empower Field Staff | TBD | TBD
Goal 5 | Conduct Plan Satisfication Survey - Solicit feedback from members about the current investment options and are they aware of the resources available (investment options) | MPERA Education and Empower Marketing Staff | 2021-12-01 | Mid December 2021 |  | Incorporate these questions in the plan satisfaction survey to retrieve data quickly
Goal 5 | Review Survey Data | MPERA, Empower, and RVK | 2022-01-01 | 2022-01-15 |  |  | Review and evaluate survey data in preparation for investment review
Goal 5 | Present survey data to board | Patty | Mid February | Mid February
Goals 4 and 5 | Evaluate Empowers available channels for requesting distributions (functionality) | Empower/Chris Heisel | 2022-01-01 | 2022-03-31 |  | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
Goal 5 | Review the procedures for conducting roll-ins and possible changes that can facilitate processing and increase ease of use and understanding for participants (functionality) education campaign benefits of rollover/keeping money together | Empower/Chris Heisel | 2022-01-01 | 2022-03-31
Goals 4 and 5 | Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) what age group/all age groups? phone or form, installment payments, one time lump sum cash out vs. rollover | Empower/Brett Fisher | 2022-02-01 | 2022-03-31
Goals 4 and 5 | Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | MPERA education and Empower Field Staff | TBD | TBD |  | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
Goals 4 and 5 | Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | Empower Field Team | TBD | TBD |  | EIAC meeting with RRR
Goals 4 and 5 | Website expected update - Empower (edu and tools) | Empower Field Team | TBD | TBD |  | When is the rollout of the new/update website expected?

## DC Long Term Plan
PERS-DC Retirement Readiness 3 year plan
| Goal 1 - Ann | Goal 2 - Patty | Goal 3 - Patty
| Increase Plan Awareness | Create Retirement Friendly DC Plan | Retain Terminated Participants
12-month goal(s) | Develop a pilot education plan for new PERS members to affect an increase in active plan election. | Optimize investment menu. Determine if MPERA wants to adopt retirement readiness advice services via Empower. Determine the distribution of our members in relation to Retirement Tiers 1-3. | Survey individuals whom refunded their PERS-DC accounts to understand why they left the plan. Determine if MPERA will adopt Empowers retirement readiness advice services; if so, execute adoption within 12 months
3-year goal(s) | Observe a 10% increase in active retirement plan elections over 3 years | Determine the optimal engagement level of the PERS DC plan | Decrease 5% of rollovers out of the plan. Identify successful outreach techniques.
Strategies | Virtual/In-person retirement education, educational campaigns, automate correspondence | Surveys, evaluation of investment menu, review of advice services, review and enhance education and tools | Surveys, retirement education campaigns highlighting resources available, offer retirement readiness advice services via 1:1 meetings
Measurements | Observable increase in plan choice elections as a direct result of strategies deployed | Thorough review and completion of Plan Sponsor Checklist including: Plan functionality, Tools, Education, Investment Menu, Default Option, Advice | Observable rate of increase in rollovers into the plan/decrease of rollovers out of the plan as a direct result of strategies deployed
Project Tasks for Year 1 of 3
January 2022 - December 2022
Project Goal | Task | Assigned To | Estimated Start Date | Estimated Finish Date | Priority | Notes | Action Items
Goal 1 | Run report on 2021 plan choice election default rates | Patty | 2021-11-01 | 2022-02-02 |  | 12/22/2021 - Query has been created. Ann looking at data.
Goal 1 | Select 10 employers to interview how they communicate retirement benefits with new employees. | MPERA | 2022-02-01 | 2022-02-28 |  | Select 10 employers that represent the diversity found throughout the state (large, small, county, city, state, school, etc.) | Yellowstone County, Flathead County/City of Kalispell
Goal 1 | Develop interview questions | MPERA | 2021-11-01 | 2022-02-15
Goal 1 | Interview employers | MPERA | 2022-03-01 | 2022-05-31 |  | Learn methods of effective communication with their employees; Would the employers be willing to communicate on our behalf to the employees
Goal 1 | Develop NEO/Education model for these 10 employers based on the feedback received from interviews | MPERA | 2022-06-01 | 2022-08-01
Goal 1 | Develop a correspondence plan for new hires based on the feedback received from interviews | MPERA | 2022-06-01 | 2022-08-01 |  | Develop plan for correspondence for new hires. How often should MPERA remind individuals of plan choice elections: every 3, 6, 9 months? How should the correspondence be delivered? What should it include? This complements 457b Goal 3 correspondence plan.
Goal 1 | Finalize the pilot program for launch in year 2 | MPERA | 2022-08-01 | 2022-11-01
Goal 1 | Analyze outcomes | MPERA | 2023 | 2023
Goal 2 | Review investment menu (investment options) | MPERA, EIAC, RVK, PRB | 2021-10-01 | 2022-10-01 |  | Investment menu is currently under review. Does the plan offer a range of investment solutions suitable for retirees? Is the Plan's default investment option suitable for retirees?
Goal 2 | Review plans fees and relative competitiveness for retirees (investment options) | MPERA, EIAC, RVK, PRB | 2021-10-01 | 2022-10-01
Goals 2 and 3 | Present Retirement Readiness Review/Advice Option to EIAC (investment options) | Liz | 2021-10-28 | 2021-10-28 |  | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
Goals 2 and 3 | Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | Patty/Liz | 2021-12-09 | 2021-12-09
Goals 2 and 3 | If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | Empower Marketing Staff | TBD | TBD
Goals 2 and 3 | If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | MPERA education and Empower Field Staff | TBD | TBD
Goal 2 | Conduct Plan Satisfication Survey - Solicit feedback from members about the current investment options and are they aware of the resources available (investment options) | MPERA Education and Empower Marketing Staff | 2021-12-01 | Mid December |  | Incorporate these questions in the plan satisfaction survey to retrieve data quickly
Goal 2 | Review Survey Data | MPERA, Empower, and RVK | 2022-01-01 | 2022-01-15 |  |  | Review and evaluate survey data in preparation for investment review
Goal 2 | Present survey data to board | Patty | Mid February | Mid February
Goals 2 and 3 | Evaluate Empowers available channels for requesting distributions (functionality) | Empower/Chris Heisel | 2022-01-01 | 2022-03-31 |  | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
Goal 2 | Review the procedures for conducting roll-ins and possible changes that can facilitate processing and increase ease of use and understanding for participants (functionality) education campaign benefits of rollover/keeping money together | Empower/Chris Heisel | 2022-01-01 | 2022-03-31
Goals 2 and 3 | Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) what age group/all age groups? phone or form, installment payments, one time lump sum cash out vs. rollover | Empower/Brett Fisher | 2022-02-01 | 2022-03-31
Goal 3 | Year end review | MPERA Education and Empower Field/Marketing Staff | 2022-12-01 | 2021-12-31
Goals 2 and 3 | Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | MPERA education and Empower Field Staff | TBD | TBD |  | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
Goals 2 and 3 | Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | Empower | TBD | TBD |  | EIAC meeting with RRR
Goals 2 and 3 | Website expected update - Empower (edu and tools) | Empower | TBD | TBD |  | When is the rollout of the new/update website expected?
Goal 3 | Learn how Empower interacts with terminating individuals (with and without RSG/Retirement Advice Services) provide options, final deferral, stay in the plan, distribution options. We do not get term dates, only know an employee is terminating when they reach out. Can MPERA input term dates on a monthly basis, or provide list of term'd ppts? We are losing assets due to uninformed participants - lack of communication. | Empower Field Team and MPERA | 2022-01-01 | 2022-03-31 |  | Learn about Empowers field experience, understand the conversation between Empower/Member | Bi-weekly field team meeting - Empower to educate MPERA
Goals 2 and 3 | Evaluate Empowers available channels for requesting distributions (functionality) | Empower/Chris Heisel | 2022-01-01 | 2022-03-31 |  | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
Goals 2 and 3 | Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) what age group/all age groups? phone or form, installment payments, one time lump sum cash out vs. rollover | Empower/Brett Fisher | 2022-02-01 | 2022-03-31
Goal 3 | Identify individuals who refunded their PERS DC account in the last 36 months include age, distribution amount/portion of account (did they set up p-pay or lump sum) | Empower/Julie Lucas | 2022-01-01 | 2022-03-31 |  | Did COVID influence termination and refunds? | Empower/MPERA mgmt to determine query of refunded individuals
Goal 3 | Create survey for individuals who refunded their PERS DC account in the last 36 months | Empower | 2022-01-01 | 2022-02-28
Goal 3 | Conduct survey individuals who refunded their PERS DC account in the last 12 months. | Empower | 2022-03-01 | 2022-03-31 |  | Begin to understand why terminated individuals leave the plan. Are pre-retirees aware of the Plan's partial distribution features? Are they aware of retirement resources available to them (counselors, webinars, and tools)?
Goal 3 | Review survey data | MPERA, Empower, RVK | 2022-04-01 | 2022-04-30 |  |  | Timeline prepares us to launch new campaign, tools, etc for 2023
Goals 2 and 3 | Present Retirement Readiness Review/Advice Option to EIAC (investment options) | Liz | 2021-10-28 | 2021-10-28 |  | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
Goals 2 and 3 | Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | Patty/Liz | 2021-12-09 | 2021-12-09
Goals 2 and 3 | If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | Empower Marketing Staff | TBD | TBD
Goals 2 and 3 | If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | MPERA education and Empower Field Staff | TBD | TBD
Goals 2 and 3 | Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | MPERA education and Empower Field Staff | TBD | TBD |  | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
Goals 2 and 3 | Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | Empower Field Team | TBD | TBD |  | EIAC meeting with RRR
Goals 2 and 3 | Website expected update - Empower (edu and tools) | Empower Field Team | TBD | TBD |  | When is the rollout of the new/update website expected?

## 457b Goal 1
Goal 1: Improve Employer Participation - Joel
12 month goal: Reach out to all non-participating employers with 10 or more employees. Survey non-participating employers to learn why they are not participating.
| Tasks (12-month) | Start Date | Finish Date | Assigned to: | Additional Notes | Actions | Results
Task 1 | 1. Reach out to all non-participating employers with 10 or more employees. Survey non-participating employers to learn why they are not participating. | 2021-11-01 | 2021-12-31 | MPERA Education | Need to identify the most appropriate contact for employer surveys for usable/strong data. This will likely be different for each employer. | Run primary and secondary active contacts in PERIS for each Org. | Query Completed/Contact List is complete 12/6/21. JT
Task 2 | 2. Create survey for non-participating employers to learn why they may not be participating | 2021-11-01 | 2021-12-31 | MPERA Education and Empower |  | Joel to research/create questions. Ask Empower for similar surveys from other contracts.
2.1 | Purchase licence for Survey Monkey | 2021-11-01 | 2021-12-31 | MPERA
2.2 | Complete survey question draft |  | 2021-12-24 | MPERA Education and Empower
2.3 | Build survey in Survey Monkey |  | 2021-01-15 | Jenn & Joel
2.4 | ITT give us non-participating employer emails | 2022-12-01 | 2022-12-31 | Ann
2.5 | Build email and update list for GovDelivery | 2022-01-10 | 2022-01-15 | Joel
Task 3 | Conduct survey for non-participating employers to learn why they may not be participating | 2022-01-15 | 2022-02-15 | MPERA Education |  | Release survey via Survey Monkey (purchase survey monkey license) using Gov Delivery
| Send reminder - follow-up email |  | 2022-02-01
Task 4 | 3. Review survey data (non participating employer; participating employer) | 2022-02-15 | 2022-03-01 | MPERA Education and Empower Marketing Staff, RVK | Extract usable data from each survey to determine new/revised education, education campaigns | Education to complete initial review, bring in Empower Marketing to review for additional content to letter (if necessary). Review survey data for participating employers to develop educational campaigns for employers.
Task 5 | 4. Develop a "Why Join" Letter recruiting Employers | 2022-03-01 | 2022-03-31 | MPERA Education and Empower Marketing Staff | This letter should highlight the benefits for employees who elect to join 457b | Use existing 'Why Join' doucment developed in 2021. Add additional information as needed, based on survey data.
Task 6 | 5. Release "Why Join" Letter to Employers | 2022-04-01 | 2022-04-01 | MPERA Education |  | Deliver to employers via email.
Task 7 | 6. Employer Spring Training - Highlight 457b Plan Education | Mid/Late April | Mid/Late April | MPERA Education |  | Provide employer 457b education as a part of employer spring training week
Task 8 | 7. Create and release follow up letter to non-participating Employers | 2022-05-15 | 2022-05-30 | MPERA Education | Offer to provide education to employer, answer question | Follow up email to non-participating employers with regard to 457b
Task 9 | 8. Report new employer 457b participation to Board and EIAC at year end | 2022-12-01 | 2022-12-31 | Patty
3 Year Goal: On an annual basis, measuring number of employers who transition, 2 employers per year.
| Tasks (3-year) | Start Date | Finish Date | Assigned to: | Additional Notes | Actions

## 457b Goal 2
Goal 2 Increase Savings Rate of Younger Participants - Jenn
12 Month Goal: Develop educational campaigns to enable Millenials and Gen Z participants to increase 457b saving rates
| Objectives (12-month) | Start Date | Finish Date | Assigned to: | Additional Notes | Progress
| Need to define 'low saving rates' |  |  |  | 604 participants increased deferrals (across all age classes) as of 11/19/2021 (2021)
| Look at the average saving rates for age group | 2021-11-19 | 2021-11-30 | Empower
| Establish current average savings rates for 39 and under | Jan. 2022 | Jan. 2022 | Empower
| Establish the current number of participants age 39 | Jan. 2022 | Jan. 2022 | Empower
| Identify data we have, need, and want to drive the goal | 2021-11-19 | 2021-12-31 | MPERA and Empower | Julie and Scott to research current data and past data of savings rates | Data has been received and reviewed (12/20/2021)
| Change scope to target specific generations in the work place | 2022-01-06 | 2022-01-06 | MPERA | See the recent Empower Study discussing patterns of behavior by generation | Review of survey complete
| Changing to generational lens - Request revision of data from Empower | 2022-01-06 | 2022-01-31 | Scott | Minllenials and Gen Z | Requested revision of 457b data to reflect saving rates by generation - Capture 2021
Task 1 | Create survey for individuals under age 39 whom are participating in 457(b) | 2022-01-15 | 2022-03-31 | MPERA Education and Empower Field/Marketing Staff | Why are individuals not invested in TDF? What is driving low 457b savings rates? Are members investing elsewhere? Do members lack understanding of optimal savings rates? Do members have lack income? Survey to learn more about this demographic of members and to determine next steps to assist in increased savings
1 | Determine if survey is necessary | 2021-12-14 | 2022-01-14 | MPERA and Empower | We may already have the data we need for low participation rates - review Empower Study discussing patterns of behavior by generation over the last 2 years | Survey has been eliminated. This has been determined unnecessary based on recent study conducted by Empower and participant behaivors. This study provides information on participant behaviors and engagnement per generation
1.1 | Cross-tabbing from customer satisifcation survey | 2022-01-15 | 2022-02-01 | Empower - Lisa | Q3, Q4, Age Q - can we crosstab customer satisifcation survey
1.2 | Complete survey question draft | 2022-02-01 | 2022-02-28 | MPERA and Empower Communications/Field staff
1.3 | Identify all 457b members under the age of 35 via query | 2022-02-01 | 2022-02-28 | Empower | Would MPERA or Empower be best to run this query?
1.4 | Build survey in Survey Monkey | 2022-03-01 | 2022-03-15 | Empower
1.5 | Build survey (email) communication | 2022-03-01 | 2022-03-15 | MPERA and Empower Communications
1.6 | Create a reminder (email) communication | 2022-03-01 | 2022-03-15 | MPERA and Empower
Task 2 | Conduct survey for individuals under age 39 whom are participating in 457(b) | 2022-04-04 | 2022-04-30 | MPERA Education and Empower Marketing Staff | If determined we do not need a survey Task 1-3 will be removed.
2.1 | Send survey email to distribution list | 2022-04-04 | 2022-04-04 | Empower
2.2 | Send a reminder email to all eligible survey participants | 2022-04-18 | 2022-04-18 | Empower
2.3 | Close survey | 2022-04-22 | 2022-04-22 | Empower
Task 3 | Review survey data (younger participants) | 2022-05-01 | 2022-05-31 | MPERA Education and Empower Marketing Staff | Extract usable data from each survey to determine new/revised education, education campaigns
3.1 | Run survey report | 2022-05-01 | 2022-05-07 | Empower
3.2 | Compile data into a report | 2022-05-07 | 2022-05-15 | Empower
3.3 | Identify trends and behaviors of members from survey data | 2022-05-15 | 2022-06-01 | MPERA Education and Empower
3.4 | Identify key areas for education | 2022-05-15 | 2022-06-01 | MPERA Education and Empower
Task 2 | Establish educational campagins for 2022 | 2022-01-15 | 2022-02-15 | MPERA and Empower Marketing Staff | Of those individualks who feel they are not contributing enough to their 401(k)s (all respondents): 53% said they need to make ends meet (budget campagin) 42% said paying off debt is holding them back (debt management/budget campaign) 14% said contributing to their 401(k) isnt a priority right now (Importance of time campaign) | Gen X: 1965-1982 (possibly remove Gen X as they are reaching their 40th year), Millennials: 1983-1995, Gen Z: 1996 or later - Focus on Millennials and Gen Z
2.1 | Identify 2022 campaigns, timelines, and components of each campaign | 2022-01-15 | 2022-02-15 | MPERA and Empower Marketing Staff | Saving Obstacles for Gen Z: 49% not saving enough due to having to make ends meet 27% said it just isnt a priority right now More likely to get help from friends, family and colleagues for savings rates (increase educaton in the work place) Resource Campaign? Saving Obstacles for Millennials: 50% paying off debt is a big factor holding them back More likely to use finanical advisors to help with savings rates (adopt Empowers advice services)
2.2 | Campaign Q1: America Saves Week | 2022-01-21 | 2022-02-25 | MPERA Education, Empower Marketing and Field Staff
2.3 | Save-Cation Themed e-mail - Develop | 2022-01-21 | 2022-02-04 | Lisa and Lori
2.4 | Identify e-mail participant list | 2022-01-21 | 2022-02-01 | Lori
2.4 | Determine Webinar for America Saves Week | 2022-01-21 | 2022-01-26 | Jenn and Julie
2.5 | Develop MPERA website banner | 2022-01-21 | 2022-02-11 | Jenn and Ann
2.6 | Develop Facebook Posts for America Saves More Week | 2022-01-21 | 2022-02-11 | MPERA Education
2.7 | Send Save-Cation Email | 2022-02-16 | 2022-02-17 | Lori and Lisa
2.8 | Host Save More Webinar(s) | 2022-02-21 | 2022-02-25 | Empower Field Team
2.9 | Facebook 'America Saves More' Posts | 2022-02-21 | 2022-02-25 | Jenn
2.1 | Campaign Engagement Data Review | 2022-03-01 | 2022-03-31 | MPERA Education, Empower Marketing and Field Staff
Task 3 | Develop increase 457b savings campaign for NRSM | 2022-06-01 | 2022-08-01 | MPERA Education and Empower Marketing Staff
3.1 | Develop campagin theme for NRSM (457b focus - consult Goal 3) | 2022-06-01 | 2022-06-30 | MPERA Education and Empower Marketing Staff
3.2 | Idenitfy training for NRSM | 2022-06-01 | 2022-06-30 | MPERA Education and Empower Field/Marketing Staff
Task 4 | NRSM Campaigns | Mid October | Mid October | MPERA Education and Empower Field Staff
4.1
Task 5 | Year end review | 2022-12-01 | 2022-12-31 | MPERA Education and Empower Field/Marketing Staff
5.1
3 Year Goal: Observe 5% of participants increase their 457b savings. Identify successful outreach techniques.
| Objectives (3-year) | Start Date | Finish Date | Assigned to: | Additional Notes | Progress

## 457b Goal 3
Goal 3 Increase Enrollments in 457(b) - Terry
12 Month Goal: Conduct surveys to targeted groups to learn why individuals are not participating in 457b. Conduct survey for participating employers to learn their level of understanding of the 457b plan and resources.
Goal 3.1 | Task | Assigned to | Start Date | Finish Date | Complete | Notes | Actions | Results
Task 1 | Run query on Yellowstone Particpation Rate | Patty | 2021-11-02 | 2021-11-02 |  |  |  | 773 Employees/ 119 Participating (15%)
Task 2 | Connect with Yellowstone County to learn about their experience transitioning to State of MT 457b, their ongoing success and struggles | Joel - set up time with Dwight Vigness and Lyndee Schmidt, include Julie, Patty | 2021-10-01 | 2021-11-15 |  | Ask Yellowstone County: What was their motivation to join State of MT 457b plan? What is important to the employer? Where are our blind spots? How can we (MPERA/Empower) improve; administratively, services, resources, education, etc.? | MPERA Edu (Terry) and Empower Field (Julie) to coordinate | Meeting Scheduld on 11-4-21. JT
|  | Joel set up questions in Word doc and send out for feedback | 2021-11-02 | 2021-11-05 |  | Set Up Questions pre-meeting - Are they satified with the level of service they are receiving? Do they think their participation has increased? What can we do differently? Do they have someone who wants to be on EIAC? Have virtual trainings been effective? How does Yellowstone County talk about retirement when onboarding (all systems). Would you recommend the State of Montana 457(b) to ther employers? Do they know why participations rates increase, decrease, stay the same? Do their members receive our communications? How much are you promoting the plan? Has MPERA offered proper support? Do they have any questions or concerns about retirement processes either as employer or on behalf of the employees? Do they have any questions they'd like to ask? | Met virtually Monday, November 8th at 4pm. | Shared with Field Staff/Patty completed 11-8-21 JT.
Task 3 | Yellowstone County Conversation - Joel set up | Patty, Joel, Julie, Dwight, Lyndee | 2021-11-08 | 2021-11-08 |  | Met virtually Monday, November 8th at 4pm. | Do we let the employer know what we're doing? What have MPERA/Empower offered over the last year and half | Met @4pm 11-8-21 JT
Task 4 | Compile what we learned | Joel, Terry Patty | 2021-11-08 | 2021-12-30 |  | Joel provided email that had meeting notes that allowed to get some take aways for improving communications with Empower. 1. They would like a meeting again in 6 months. 2. Working to resolve ongoing reporting issues and enrollment/deferral issues.3. Improved communication between the county and MPERA, Empower. Education/Training for employees via in-person, virtual and pre-recorded. 12-9-21 | 1.Set up calendar event to schedule 6 month check in with Yellowstone County with MPERA and HR | 1. Done 12/9
Goal 3.2 | Conduct 457(b) employer query to ID the best contact at each location for survey | MPERA Education |  |  |  | Need to identify the most appropriate contact for employer surveys for usable/strong data. This will likely be different for each employer. | Run primary and secondary active contacts in PERIS for each Org.
Task 5 | Create an ITT to query PERIS by 457(b) employer for all active contact information | Joel will determine best contact | 2021-11-01 | 2021-12-31 |  | Joel has it under Planning Meetings/Contact information | Exclude VFCA, non-participating employers.
| Create survey for participating employers to understand the employers level of understanding of the 457b plan | Liz, Scott, Empower Field Staff, MPERA Education | 2021-10-15 | 2021-12-31 |  | 12-9-2021 updated the survey, need to review in next RR meeting. TD | Sent over by Scott
| Conduct survey for participating employers | MPERA Education | 2022-01-15 | 2022-02-15 |  | A Survey Monkey license has been purchased. Jenn has added our license and login information to the network in our planning meeting folder (see the Word document). L/Planning Meetings/Survey Monkey Info | Release survey via Survey Monkey (purchase survey monkey license) using Gov Delivery
| Review survey data (non participating employer; participating employer) | MPERA Education and Empower Marketing Staff | 2022-02-15 | 2022-03-01 |  |  | Education to complete initial review, bring in Empower Marketing to review for additional content to letter (if necessary). Review survey data for participating employers to develop educational campaigns for employers.
| Employer Spring Training - Highlight 457b Plan Education | MPERA Education | Mid/Late April | Mid/Late April |  |  | Provide employer 457b education as a part of employer spring training week
| Create and release follow up letter to participating Employers | MPERA Education | 2022-05-15 | 2022-05-30
| Create survey for individuals who are NOT participating in 457(b) individuals under 35 and new hires over 35 | MPERA Education and Empower Field/Marketing Staff | 2022-06-01 | 2022-07-01 |  | Ask for demographic info in the survey. | Ask Empower if they have previous survey questions to leverage.
| Run query for non-participating and eligible 457b participants under 35 and new hires over 35 | MPERA Education | 2022-06-01 | 2022-07-01 |  |  | Query in PERIS
| Conduct survey for individuals who are NOT participating in 457(b) | MPERA Education | 2022-07-01 | 2022-07-30 |  |  | Via Gov Delivery using Survey monkey
| Review survey data | MPERA Education and Empower Field/Marketing Staff | 2022-08-01 | 2022-08-15 |  | Extract usable data from each survey to determine new/revised education, education campaigns | Education to complete initial review, bring in Empower Marketing to review for additional content to letter (if necessary)
| Develop 457b enrollment campagin for NRSM | MPERA Education and Empower Field/Marketing Staff | 2022-08-15 | 2022-09-15
| NRSM Campaign | MPERA Education/Empower Field Staff | Mid October | Mid October
| Year end review | MPERA Education and Empower Field/Marketing Staff | 2022-12-01 | 2022-12-31
| Start conversations with employers about how to engage and connect with all new hires regardless of age | MPERA Education | 2023 | 2023 |  | NEOs are a key variable to initial engage with new hires. Suggested to follow up with new hires shortly after NEOs. Younger generations are connecting with data that demonstrates the importance of saving now versus later. Compounding interested over time is resonating with younger generations. Strengthen relationship with Employers to lead to greater engagement with employees. | Maybe Feb 2023 Fall in Love with 457b Campaign?
Goal 3 | Develop a correspondence plan for all new hires | MPERA Education and Empower Marketing Staff | 2023 | 2023 |  | Develop plan for correspondence for new hires. How often should MPERA reach out to new hires? Every 3, 6, 9 months? How should the correspondence be delivered? Younger generations - consider e-mail, social media, videos, etc. What should it include? This effort can be combined with new hire plan choice election correspondence. Separate communication for other retirement systems. | Maybe Feb 2023 Fall in Love with 457b Campaign?

## 457b Goal 4
Goal 4: Retain Terminated Participants - Patty
12 month goal: Survey individuals whom refunded their 457b accounts to understand why they left the plan. Determine if MPERA will adopt Empowers retirement readiness advice services; if so, execute adoption within 12 months.
| Tasks (12-month) | Start Date | Finish Date | Assigned to: | Additional Notes | Actions | Results
Task 1 | Learn how Empower interacts with terminating individuals (with and without RSG/Retirement Advice Services) | 2022-01-01 | 2022-03-31 | Empower and MPERA | Learn about Empowers field experience, understand the conversation between Empower/Member | Bi-weekly field team meeting - Empower to educate MPERA
Task 2 | Evaluate Empowers available channels for requesting distributions (functionality) | 2022-01-01 | 2022-03-31 | Empower | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
Task 3 | Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) | 2022-02-01 | 2022-03-31 | Empower
Task 4 | Identify individuals who refunded their 457b account in the last 12 months | 2022-01-01 | 2022-01-31 | Empower | Did COVID influence termination and refunds? | Empower/MPERA mgmt to determine query of refunded individuals
| Create survey for individuals who took a full their 457b account in the last 12 months | 2022-01-01 | 2022-02-15 | Empower/MPERA
| Conduct survey individuals who refunded their 457b account in the last 12 months. | 2022-03-01 | 2022-03-31 | Empower | Begin to understand why terminated individuals leave the plan. Are pre-retirees aware of the Plan's partial distribution features? Are they aware of retirement resources available to them (counselors, webinars, and tools)? Lisa has distribution questions that she can share. Jan 1st - Dec 31st 2021 - FN, LN, email address, amount of w/d, age, withdrawl reason, payable? was it a rollover or full withdrawal to self.
| Survey Participants | 2022-03-01 | 2022-03-15 | MPERA
| Review survey data | 2022-04-01 | 2022-04-30 | MPERA, Empower, RVK |  | Timeline prepares us to launch new campaign, tools, etc for 2023
Task 5 | Present Retirement Readiness Review/Advice Option to EIAC (investment options) | 2022-01-27 | 2022-01-27 | Mary Beth | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
1. They confirmed that Advise services are tied to managed accounts at the Plan level. We could implement some RSG services that include advise but would lose the tools available on the web and getting the field reps to work as advisors and has to do with the underlying platform that runs advise and managed accounts.
2. They will provide us with sample reports of the plan outcomes that we should be looking at as the fiduciary. We asked for information on plans that currently have advise/managed accounts and what the outcomes are, what is the ‘uptake’ % on managed accounts.
3. They will provide us with an outline of member conversation form and site personalization, follow-up on personalization and effectiveness of the conversations.
4. They will provide us with documentation on the number of participants that stay with managed accounts, or roll out after termination from employment, and the number of members who stay after termination when they have received advise.
5. They will provide us with sample communications on the services, annually, quarterly, etc.
6. Elise asked if employees where bonused for services. They confirmed that their employees have “meeting goals” and other performance incentives, but they are not bonused for recommending managed accounts.
| Advise Services Presentation to Education Team | 2022-01-24 | 2022-01-28 | MPERA, Empower | In person web demo with Education staff and Empower Field Staff.
Task 6 | Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | 2021-12-09 | 2021-12-09 | Patty/Liz | Dependent on EIAC decision 01/27/2022
| If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | TBD | TBD | Empower Marketing Staff
| If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | TBD | TBD | MPERA education and Empower Field Staff
| Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | TBD | TBD | MPERA education and Empower Field Staff | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
| Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | TBD | TBD | Empower | EIAC meeting with RRR
| Website expected update - Empower (edu and tools) | TBD | TBD | Empower | When is the rollout of the new/update website expected?
3 Year Goal:Increase 5% of rollovers into the plan. Decrease 5% of rollovers out of the plan. Identify successful outreach techniques.
| Tasks (3-year) | Start Date | Finish Date | Assigned to: | Additional Notes | Actions

## 457b Goal 5
Goal 5: Create Retirement Friendly 457(b) Plan - Patty
12 month goal: Optimize investment menu. Determine if MPERA wants to adopt Empower retirement readiness advice services. Determine the distribution of our members in relation to Retirement Tiers 1-3.
| Tasks (12-month) | Start Date | Finish Date | Assigned to: | Additional Notes | Actions | Results
Task 1 | Learn how Empower interacts with terminating individuals (with and without RSG/Retirement Advice Services) | 2022-01-01 | 2022-03-31 | Empower and MPERA | Learn about Empowers field experience, understand the conversation between Empower/Member | Bi-weekly field team meeting - Empower to educate MPERA
Task 2 | Evaluate Empowers available channels for requesting distributions (functionality) | 2022-01-01 | 2022-03-31 | Empower | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
Task 3 | Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) | 2022-02-01 | 2022-03-31 | Empower
Task 4 | Identify individuals who refunded their 457b account in the last 12 months | 2022-01-01 | 2022-01-31 | Empower | Did COVID influence termination and refunds? | Empower/MPERA mgmt to determine query of refunded individuals
| Create survey for individuals who refunded their 457b account in the last 12 months | 2022-01-01 | 2022-02-28 | Empower
| Conduct survey individuals who refunded their 457b account in the last 12 months. | 2022-03-01 | 2022-03-31 | Empower | Begin to understand why terminated individuals leave the plan. Are pre-retirees aware of the Plan's partial distribution features? Are they aware of retirement resources available to them (counselors, webinars, and tools)?
| Review survey data | 2022-04-01 | 2022-04-30 | MPERA, Empower, RVK |  | Timeline prepares us to launch new campaign, tools, etc for 2023
Task 5 | Present Retirement Readiness Review/Advice Option to EIAC (investment options) | 2022-01-27 | 2022-01-27 | Liz | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
| EIAC - Planning and Presentation Information Meeting | 2022-01-07 | 2022-01-07 | MPERA, Empower, RVK
1. They confirmed that Advise services are tied to managed accounts at the Plan level. We could implement some RSG services that include advise but would lose the tools available on the web and getting the field reps to work as advisors and has to do with the underlying platform that runs advise and managed accounts.
2. They will provide us with sample reports of the plan outcomes that we should be looking at as the fiduciary. We asked for information on plans that currently have advise/managed accounts and what the outcomes are, what is the ‘uptake’ % on managed accounts.
3. They will provide us with an outline of member conversation form and site personalization, follow-up on personalization and effectiveness of the conversations.
4. They will provide us with documentation on the number of participants that stay with managed accounts, or roll out after termination from employment, and the number of members who stay after termination when they have received advise.
5. They will provide us with sample communications on the services, annually, quarterly, etc.
6. Elise asked if employees where bonused for services. They confirmed that their employees have “meeting goals” and other performance incentives, but they are not bonused for recommending managed accounts.
| Advise Services Presentation to Education Team | 2022-01-24 | 2022-01-28 | MPERA, Empower | In person web demo with Education staff and Empower Field Staff.
Task 6 | Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | 2022-02-10 | 2022-02-10 | Patty/Liz
| If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | TBD | TBD | Empower Marketing Staff
| If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | TBD | TBD | MPERA education and Empower Field Staff
| Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | TBD | TBD | MPERA education and Empower Field Staff | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
| Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | TBD | TBD | Empower | EIAC meeting with RRR
| Website expected update - Empower (edu and tools) | TBD | TBD | Empower | When is the rollout of the new/update website expected?
3 Year Goal: Determine the optimal engagement level of the 457(b) plan
| Tasks (3-year) | Start Date | Finish Date | Assigned to: | Additional Notes | Actions
| Review investment menu (investment options) | 2021-10-01 | 2022-10-01 | MPERA, EIAC, RVK, PRB | Investment menu is currently under review. Does the plan offer a range of investment solutions suitable for retirees? Is the Plan's default investment option suitable for retirees?
| Review plans fees and relative competitiveness for retirees (investment options) | 2021-10-01 | 2022-10-01 | MPERA, EIAC, RVK, PRB | Completed with recent fee changes? OR was this to target younger participants?
| Present Retirement Readiness Review/Advice Option to EIAC (investment options) | 2021-10-28 | 2021-10-28 | Liz | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
| Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | 2022-02-10 | 2022-02-10 | Patty/Liz | Dependent on EIAC decision 01/27/2022
| If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | TBD | TBD | Empower Marketing Staff
| If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | TBD | TBD | MPERA education and Empower Field Staff
| Conduct Plan Satisfication Survey - Solicit feedback from members about the current investment options and are they aware of the resources available (investment options) | 2021-12-01 | Mid December 2021 | MPERA Education and Empower Marketing Staff | Incorporate these questions in the plan satisfaction survey to retrieve data quickly
| Review Survey Data | 2022-01-01 | 2022-01-15 | MPERA, Empower, and RVK |  | Review and evaluate survey data in preparation for investment review
| Present survey data to board | Mid February | Mid February | Patty
| Evaluate Empowers available channels for requesting distributions (functionality) | 2022-01-01 | 2022-03-31 | Empower | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
| Review the procedures for conducting roll-ins and possible changes that can facilitate processing and increase ease of use and understanding for participants (functionality) | 2022-01-01 | 2022-03-31 | Empower
| Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) | 2022-02-01 | 2022-03-31 | Empower
| Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | TBD | TBD | MPERA education and Empower Field Staff | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
| Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | TBD | TBD | Empower | EIAC meeting with RRR
| Website expected update - Empower (edu and tools) | TBD | TBD | Empower | When is the rollout of the new/update website expected?

## PERS DC Goal 1
PERS DC Goal 1 Increase Plan Awareness - Ann
12 Month Goal: Develop a pilot education plan for new PERS members to affect an increase in active plan election.
Tasks |  | Assigned To | Estimated Start Date | Estimated Finish Date | Actual Finish Date | Notes | Action Items
Task 1 | Run report on 2021 plan choice election default rates | Patty | 2021-11-01 | 2022-12-10
1.1 | Develop a new query to determine default rates and employers | Patty, Ann, Judekay | 2021-12-03 | 2021-12-10 | 2021-12-21 | Report percentages, during a specific time frame, University vs non-university. | ITT 18945 We need a new query to determine the default rate and the number of plan choice elections during a fiscal year. Person ID, First Name, Last Name, Employer Number, Employer Name, Date of Hire There is a report that was run in IDMS that held the information. # RP9613
1.2 | Analyze the report information | MPERA Education | 2022-01-20
Task 2 | Select 10 employers to interview how they communicate retirement benefits with new employees. | MPERA Education | 2022-02-01 | 2022-02-28 |  | Select 10 employers that represent the diversity found throughout the state (large, small, county, city, state, school, etc.)
Task 3 | Develop interview questions | MPERA Education | 2021-11-01 | 2022-02-28
3.1 | Determine how many questions | MPERA Education
3.2 | Draft and finalize questions
3.3 | Determine contacts
3.4 | Set up interviews
Task 4 | Interview employers | MPERA | 2022-03-01 | 2022-05-31 |  | Learn methods of effective communication with their employees; Would the employers be willing to communicate on our behalf to the employees
4.1 | Review Answers | MPERA Education
4.2 | Determine if follow-up is necessary | MPERA Education
Task 5 | Develop NEO/Education model for these 10 employers based on the feedback received from interviews | MPERA | 2022-06-01 | 2022-08-01
Task 6 | Develop a correspondence plan for new hires based on the feedback received from interviews | MPERA | 2022-06-01 | 2022-08-01 |  | Develop plan for correspondence for new hires. How often should MPERA remind individuals of plan choice elections: every 3, 6, 9 months? How should the correspondence be delivered? What should it include? This complements 457b Goal 3 correspondence plan.
Task 7 | Finalize the pilot program for launch in year 2 | MPERA | 2022-08-01 | 2022-11-01
Task 8 | Analyze outcomes | MPERA | 2023 | 2023
3 Year Goal: Observe a 10% increase in active retirement plan elections over 3 years
Tasks |  | Assigned To | Estimated Start Date | Estimated Finish Date | Actual Finish Date | Notes | Action Items

## PERS DC Goal 2
PERS DC Goal 2: Create Retirement Friendly DC Plan - Patty
12 Month Goal - Develop a pilot education plan for new PERS members to affect an increase in active plan election.
Tasks |  | Assigned To | Estimated Start Date | Estimated Finish Date | Actual Finish Date | Notes | Action Items
Task 1 | Review investment menu (investment options) | MPERA, EIAC, RVK, PRB | 2021-10-01 | 2022-10-01 |  | Investment menu is currently under review. Does the plan offer a range of investment solutions suitable for retirees? Is the Plan's default investment option suitable for retirees?
Task 2 | Review plans fees and relative competitiveness for retirees (investment options) | MPERA, EIAC, RVK, PRB | 2021-10-01 | 2022-10-01
Task 3 | Present Retirement Readiness Review/Advice Option to EIAC (investment options) | Liz | 2021-10-28 | 2021-10-28 |  | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
Task 4 | Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | Patty/Liz | 2021-12-09 | 2021-12-09
Task 5 | If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | Empower Marketing Staff | TBD | TBD
Task 6 | If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | MPERA education and Empower Field Staff | TBD | TBD
Task 7 | Conduct Plan Satisfication Survey - Solicit feedback from members about the current investment options and are they aware of the resources available (investment options) | MPERA Education and Empower Marketing Staff | 2021-12-01 | Mid December |  | Incorporate these questions in the plan satisfaction survey to retrieve data quickly
| Review Survey Data | MPERA, Empower, and RVK | 2022-01-01 | 2022-01-15 |  |  | Review and evaluate survey data in preparation for investment review
Task 8 | Present survey data to board | Patty | Mid February | Mid February
| Evaluate Empowers available channels for requesting distributions (functionality) | Empower | 2022-01-01 | 2022-03-31 |  | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
| Review the procedures for conducting roll-ins and possible changes that can facilitate processing and increase ease of use and understanding for participants (functionality) | Empower | 2022-01-01 | 2022-03-31
| Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) | Empower | 2022-02-01 | 2022-03-31
| Year end review | MPERA Education and Empower Field/Marketing Staff | 2022-12-01 | 2021-12-31
| Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | MPERA education and Empower Field Staff | TBD | TBD |  | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
| Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | Empower | TBD | TBD |  | EIAC meeting with RRR
| Website expected update - Empower (edu and tools) | Empower | TBD | TBD |  | When is the rollout of the new/update website expected?
3 Year Goal: Determine the optimal engagement level of the PERS DC plan
Tasks |  | Assigned To | Estimated Start Date | Estimated Finish Date | Actual Finish Date | Notes | Action Items

## PERS DC Goal 3
PERS DC Goal 3: Retain Terminated Participants - Patty
12 Month Goal -Survey individuals whom refunded their PERS-DC accounts to understand why they left the plan. Determine if MPERA will adopt Empowers retirement readiness advice services; if so, execute adoption within 12 months
Tasks |  | Assigned To | Estimated Start Date | Estimated Finish Date | Actual Finish Date | Notes | Action Items
Task 1 | Learn how Empower interacts with terminating individuals (with and without RSG/Retirement Advice Services) | MPERA and Empower | 2022-01-01 | 2022-03-31 |  | Learn about Empowers field experience, understand the conversation between Empower/Member | Bi-weekly field team meeting - Empower to educate MPERA
Task 2 | Evaluate Empowers available channels for requesting distributions (functionality) | Empower | 2022-01-01 | 2022-03-31 |  | How do can distributions become easier for the participants? Seamless, timely, simple. All forms of distributions. MPERA to share termination and vesting data with Empower to improve distribution processes? Does this include sharing re-hire information with Empower?
Task 3 | Analyze distribution patterns of older age groups to learn about distribution behaviors (functionality) | Empower | 2022-02-01 | 2022-03-31
Task 4 | Identify individuals who refunded their PERS DC account in the last 36 months | Empower | 2022-01-01 | 2022-03-31 |  | Did COVID influence termination and refunds? | Empower/MPERA mgmt to determine query of refunded individuals
Task 5 | Create survey for individuals who refunded their PERS DC account in the last 36 months | Empower | 2022-01-01 | 2022-02-28
Task 6 | Conduct survey individuals who refunded their PERS DC account in the last 12 months. | Empower | 2022-03-01 | 2022-03-31 |  | Begin to understand why terminated individuals leave the plan. Are pre-retirees aware of the Plan's partial distribution features? Are they aware of retirement resources available to them (counselors, webinars, and tools)?
Task 7 | Review survey data | MPERA, Empower, RVK | 2022-04-01 | 2022-04-30 |  |  | Timeline prepares us to launch new campaign, tools, etc for 2023
| Present Retirement Readiness Review/Advice Option to EIAC (investment options) | Liz | 2021-10-28 | 2021-10-28 |  | Background: Alternate descriptor for managed accounts = retirement readiness review/advice. This service stresses the impact and advice given to the participants. The goal of this service is to improve retirement readiness for everyone; this is a very individualized conversation. The sessions include discussion regarding savings rates, allocations/investments, and spend down (50+). The discussion is focused on a holistic perspective including other investments including spouses retirement income.
Task 8 | Present Retirement Readiness Review/Advice Option to MPERA Board (investment options) | Patty/Liz | 2021-12-09 | 2021-12-09
Task 9 | If Retirement Readiness/Review Advice Option is adopted, establish a marketing plan for these services (investment options) | Empower Marketing Staff | TBD | TBD
Task 10 | If retirement readiness review/advice option adopted, target pre-retirees increase the focus on staying in the plan via education (investment options) | MPERA education and Empower Field Staff | TBD | TBD
Task 11 | Review targeted campaigns, printed and online resources, and group workshops for both active, inactive, and retired participants (edu and tools) | MPERA education and Empower Field Staff | TBD | TBD |  | Review effectiveness (define; what equals success) of targeted campaigns, communication methods, does the campaign reach the intended goal
Task 12 | Review retirement tools and calculators and compare offerings to others (pre-retiree/retirees)(edu and tools) | Empower | TBD | TBD |  | EIAC meeting with RRR
Task 13 | Website expected update - Empower (edu and tools) | Empower | TBD | TBD |  | When is the rollout of the new/update website expected?
3 Year Goal: Decrease 5% of rollovers out of the plan. Identify successful outreach techniques.
Tasks |  | Assigned To | Estimated Start Date | Estimated Finish Date | Actual Finish Date | Notes | Action Items